## Gantt Chart Template
Task name | Stard date | End date | Assigned | Status | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05
PROGETTO | 2025-01-27 | 2025-05-05 | Sironi | Open
Documento 1 | 2025-01-27 | 2025-01-30 | Motto | Done
Documento 2 | 2025-01-30 | 2025-02-03 | Sironi | In process
Documento 3 | 2025-02-03 | 2025-02-06 | Cazzaniga | Closed
Documento 4 | 2025-02-06 | 2025-02-10 | Donadoni | Closed
Documento 5 | 2025-02-10 | 2025-02-13 | Conti | Closed
Documento 6 | 2025-02-13 | 2025-02-17 | Spinelli | Closed
Documento 7 | 2025-02-17 | 2025-02-20 | Camnasio | Closed
Documento 8 | 2025-02-20 | 2025-02-24 | Motto | Closed
Documento 9 | 2025-02-24 | 2025-02-27 | Rigamonti | Closed
Documento 10 | 2025-02-27 | 2025-03-03 | Cazzaniga | Closed
Documento 11 | 2025-03-03 | 2025-03-06 | Donadoni | Closed
Documento 12 | 2025-03-10 | 2025-03-13 | Conti | Closed
Documento 13 | 2025-03-13 | 2025-03-17 | Spinelli | Closed
Documento 14 | 2025-03-17 | 2025-03-20 | Camnasio | Closed
Documento 15 | 2025-03-20 | 2025-03-24 | Motto | Closed
Documento 16 | 2025-03-31 | 2025-04-03 | Rigamonti | Closed
Documento 17 | 2025-04-03 | 2025-04-07 | Cazzaniga | Closed
Documento 18 | 2025-04-07 | 2025-04-10 | Donadoni | Closed
Documento 19 | 2025-04-10 | 2025-04-14 | Conti | Closed
Documento 20 | 2025-04-14 | 2025-04-28 | Spinelli | Closed
Revisione generale e consegna | 2025-04-28 | 2025-05-05 | Sironi | Closed

## Assignees and Status
Assignees | Status
Motto | Done
Rigamonti | Closed
Cazzaniga | Closed
Donadoni | Closed
Conti | Closed
Spinelli | Closed
Camnasio | Closed